GROUP ASSIGNMENT – MEETING MINUTES

| Module Name | CSCK505 Robotics July 2026 |
| --- | --- |
| Assignment Name | End of Module Assignment: A Behaviour-based Map Building Robotic System |
| Assignment Due Date | 21 September 2026, 11:59 PM |
| Team Name | Group B |

Please, list your team members’ names in the table below and their respective roles.

Depending on the project, roles could be represented by specific tasks (i.e., tests/reviews), sections (i.e., poster sections), or anything else that explicitly identifies what each member is assigned to.

This document can be used for both synchronous (live/ real-time) and asynchronous collaboration.

| Full Name | Role / Tasks |
| --- | --- |
| Bandar Alharbi | Group coordination, pull-request review, meeting minutes, video presentation. Setup GitHub |
| Pranav Arya | Report drafting and revision |
| Dramane Bako | Quality assurance, visual verification, results analytics |
| Christopher Eaton | Webot maze environments, sensor configuration, LiDAR mounting |
| Alex Senger | Coder: Robot controller, DFS navigation on logic, map generation. |

| 1. Meeting info |  |  |  |
| --- | --- | --- | --- |
| Date of Meeting (or reporting deadline) | 3 September 2026 | Time [UK] (or reporting deadline e.g. 23:55) | 13:00 |
| Location (VLE, Teams Chat for asynchronous) | MS Teams | Minutes prepared by | Bandar Alharbi |

2. Meeting Objective (task completion, challenges, future tasks)

Kick-off: analyse the assignment brief, break the work into owned tasks, set up the shared GitHub repository and agree staged deadlines.

| 3. Attendance (or reporting progress from team members within 24h window before deadline) |  |
| --- | --- |
| Full Name | Present (reported) / Not present (did not report) / Sent apologies |
| Bandar Alharbi | Present |
| Pranav Arya | Present |
| Dramane Bako | Present |
| Christopher Eaton | Present |
| Alex Senger | Present |

| 4. Agenda and Notes, Decisions, Issues |  |  |
| --- | --- | --- |
| Topic | Owner | Notes |
| Assignment analysis | All members | The group reviewed the End of Module brief: a behaviour-based robot that explores a previously unseen maze and produces a matrix map, built in Webots and tested with two distinct sensor configurations. Agreed to address the four assignment tasks in sequence, building the environment first so that controller development could proceed against a fixed specification rather than a moving one |
| Breaking the assignment down into tasks | All members | Work was split by deliverable rather than by report section, so that each member owns one piece end to end. Agreed allocation: Webots environment (Christopher), robot controller and navigation logic (Alex), quality assurance and results analytics (Dramane), written report (Pranav), video presentation and overall coordination (Bandar). |
| Adding group member to GitHub Ropo. | Bandar Alharbi | Members were asked to supply their GitHub usernames so access could be granted. |
| Setup shared Repo. | Bandar Alharbi | A private repository was created at github.com/Bandarbinsaad/csck505-group-project as the single source of truth for code, figures and documentation. Agreed that all work would be merged through pull requests with at least one reviewer, so that changes remain visible to the whole group and nothing is developed in isolation. |
| Setting Task Deadlines | All members | Staged deadlines were agreed so that each task begins from a finished input rather than running in parallel against an unstable base: environment by 7 September, controller by 12 September, quality assurance and analytics by 14 September, report draft by 15 September, video by 18 September. The next reporting checkpoint was set for 11 September and confirmed by group poll. |
| The “Notes” column should include a summary of the discussion had about the topic and any decision taken. |  |  |

| 5. Action Items |  |  |
| --- | --- | --- |
| Action | Owner | Due Date |
| Build and test the Webots maze environment, and confirm world specification, cell size, coordinate convention and device names | Chris | 7 September 2026 |
| Develop the robot controller and navigation logic for both sensor configurations | Alex | 12 September |
| Quality assurance, visual verification and results analytics | QA & Analytics | 14 September |
| Dart group report | Pravan | 15 September |
| Produce the video presentation | Bandar | 18 September |
| The “Action” section must include the action(s) that the “Owner” (the student assigned to complete the action) must complete by the due date. |  |  |

| 6. Next Meeting (or reporting deadline) |  |  |  |
| --- | --- | --- | --- |
| Date (DD/MM/YY) | 11 September 2026 | Time [UK] (HH:MM) | 13:00 |
| Location | Teams |  |  |
| Objective | Ensure tasks are on track as planned and provide support where needed. |  |  |
| Unless this minutes refers to the last one before submission, students need to identify date, location and objective of the next meeting/ reporting deadline before concluding the current meeting/ reporting deadline. |  |  |  |

A copy of this document MUST be included in your final submission. The assessment will take into account these documents: you must ensure they are updated and accurate. In case of inconsistencies, please discuss them with your peers before submitting it. If these documents result inconsistent and differ among submissions, the final grade will be negatively affected (poor engagement).