GROUP ASSIGNMENT – MEETING MINUTES

| Module Name | CSCK505 Robotics July 2026 |
| --- | --- |
| Assignment Name | End of Module Assignment: A Behaviour-based Map Building Robotic System |
| Assignment Due Date | 21 September 2026, 11:59 PM |
| Team Name | Group B |

Please, list your team members’ names in the table below and their respective roles.

Depending on the project, roles could be represented by specific tasks (i.e., tests/reviews), sections (i.e., poster sections), or anything else that explicitly identifies what each member is assigned to.

This document can be used for both synchronous (live/ real-time) and asynchronous collaboration.

| Full Name | Role / Tasks |
| --- | --- |
| Bandar Alharbi | Group coordination, pull-request review, meeting minutes, video presentation. Setup GitHub |
| Pranav Arya | Report drafting and revision |
| Dramane Bako | Quality assurance, visual verification, results analytics |
| Christopher Eaton | Webot maze environments, sensor configuration, LiDAR mounting |
| Alex Senger | Coder: Robot controller, DFS navigation on logic, map generation. |

| 1. Meeting info |  |  |  |
| --- | --- | --- | --- |
| Date of Meeting (or reporting deadline) | 19 September 2026 | Time [UK] (or reporting deadline e.g. 23:55) | 11:00 |
| Location (VLE, Teams Chat for asynchronous) | WhatsApp | Minutes prepared by | Bandar Alharbi |

2. Meeting Objective (task completion, challenges, future tasks)

Kick-off: analyse the assignment brief, break the work into owned tasks, set up the shared GitHub repository and agree staged deadlines.

| 3. Attendance (or reporting progress from team members within 24h window before deadline) |  |
| --- | --- |
| Full Name | Present (reported) / Not present (did not report) / Sent apologies |
| Bandar Alharbi | Present |
| Pranav Arya | Present |
| Dramane Bako | Present |
| Christopher Eaton | Present |
| Alex Senger | Present |

| 4. Agenda and Notes, Decisions, Issues |  |  |
| --- | --- | --- |
| Topic | Owner | Notes |
| Video presentation | Bandar Alharbi | The recorded presentation was circulated to the group for review and confirmation. It covers the two maze environments, the robot and its two sensor configurations, the depth-first navigation algorithm, the resulting occupancy maps, the timing comparison across all four runs, and the improvements the group would make with more time. |
| Meeting minutes | Bandar Alharbi | Minutes for all four reporting checkpoints were compiled and circulated for agreement, so that identical copies are included in every submission. Members were asked to raise any correction before submitting rather than amending their own copy, since inconsistent documents across submissions count against the group. |
| Submission package | All member | Agreed the package each member submits: the final report, the video presentation, the four sets of meeting minutes and the repository link. Agreed that all members submit the same agreed versions. |
| The “Notes” column should include a summary of the discussion had about the topic and any decision taken. |  |  |

| 5. Action Items |  |  |
| --- | --- | --- |
| Action | Owner | Due Date |
| Review and confirm the final report version | All members | 19 September |
| Review and confirm the video presentation | All members | 19 September |
| Agree these minutes and confirm no amendments | All members | 19 September |
| Submit the agreed report, video and meeting minutes | All members | 19 September |
| The “Action” section must include the action(s) that the “Owner” (the student assigned to complete the action) must complete by the due date. |  |  |

| 6. Next Meeting (or reporting deadline) |  |  |  |
| --- | --- | --- | --- |
| Date (DD/MM/YY) | Not Applicable | Time [UK] (HH:MM) | Not Applicable |
| Location | WhatsApp |  |  |
| Objective | This is the last reporting deadline before the submission date of 21 September 2026. |  |  |
| Unless this minutes refers to the last one before submission, students need to identify date, location and objective of the next meeting/ reporting deadline before concluding the current meeting/ reporting deadline. |  |  |  |

A copy of this document MUST be included in your final submission. The assessment will take into account these documents: you must ensure they are updated and accurate. In case of inconsistencies, please discuss them with your peers before submitting it. If these documents result inconsistent and differ among submissions, the final grade will be negatively affected (poor engagement).